## Gantt Chart
GANTT CHART TEMPLATE |  |  |  | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
WBS NUMBER | TASK TITLE | START DATE | DUE DATE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
|  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  |  | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1.1 | Idea proposing | 24/5/2019 | 27/5/2019 | bar: WEEK 1 F to WEEK 2 T
1.2 | Meeting with supervisor | 27/5/2019 | 27/5/2019 | bar: WEEK 2 W
1.3 | Proposal submission | 27/5/2019 | 31/5/2019 | bar: WEEK 2 W to WEEK 3 T
1.4 | Chapter 1 writing report | 17/6/2019 | 21/6/2019 | bar: WEEK 3 M to WEEK 3 F
1.5 | Meeting with supervisor | 26/6/2019 | 26/6/2019 | bar: WEEK 4 W
1.6 | Chapter 2 writing report | 2019-01-07 | 2019-05-07
1.7 | Meeting with supervisor | 2019-10-07 | 2019-10-07 | bar: WEEK 6 W
1.8 | Correction in Chapter 2 writing report | 2019-11-07 | 16/7/2019 | bar: WEEK 6 R to WEEK 7 R
1.9 | Meeting with supervisor | 18/7/2019 | 18/7/2019 | bar: WEEK 8 M
2 | Chapter 3 in writing report | 19/7/2019 | 24/7/2019 | bar: WEEK 8 W to WEEK 9 W
2.1 | Meeting with supervisor | 25/7/2019 | 25/7/2019 | bar: WEEK 9 R
3.1 | Status and Tracking
3.2 | KPIs
3.2.1 | Monitoring
3.2.2 | Forecasts
3.3 | Project Updates
3.3.1 | Chart Updates
2.2 | Chapter 4 in writing report | 26/7/2019 | 31/7/2019 | bar: WEEK 9 F to WEEK 10 F
2.3 | Meeting with co-supervisor | 2019-01-08 | 2019-01-08 | bar: WEEK 11 M
2.4 | Chapter 5 in writing report | 2019-02-08 | 2019-07-08 | bar: WEEK 11 M to WEEK 12 M
2.5 | Meeting with supervisor | 2019-08-07 | 2019-08-07 | bar: WEEK 12 M
2.6 | Overall correction | 2019-09-08 | 2019-12-08 | bar: WEEK 12 M to WEEK 12 R
2.7 | Meeting with supervisor | 13/8/2019 | 13/8/2019 | bar: WEEK 12 R
2.8 | FYP submission | 15/8/2019 | 15/8/2019 | bar: WEEK 12 F

## Sheet2
NO. | TASK TITLE | START DATE | DUE DATE | 2019
|  |  |  | 19/5 - 25/5 |  |  |  |  | 26/5 - 1/6 |  |  |  |  | 2/6 - 8/6 |  |  |  |  | 9/6 - 15/6 |  |  |  |  | 16/6 - 22/6 |  |  |  |  | 23/6 - 29/6 |  |  |  |  | 30/6 - 6/7 |  |  |  |  | 7/7 - 13/7 |  |  |  |  | 14/7 - 20/7 |  |  |  |  | 21/7 - 27/7 |  |  |  |  | 28/7 - 3/8 |  |  |  |  | 4/8 - 10/8 |  |  |  |  | 11/8 - 17/8
|  |  |  | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Idea proposing | 24/5/2019 | 27/5/2019 | bar: 19/5 - 25/5 F to 26/5 - 1/6 M
2 | Meeting with supervisor | 27/5/2019 | 27/5/2019 | bar: 26/5 - 1/6 M
3 | Proposal submission | 27/5/2019 | 31/5/2019 | bar: 26/5 - 1/6 M to 26/5 - 1/6 F
4 | Chapter 1 writing report | 2019-01-06 | 2019-07-06 | bar: 2/6 - 8/6 M to 2/6 - 8/6 W
5 | Chapter 2 writing report | 2019-09-06 | 13/6/2019 | bar: 2/6 - 8/6 R to 9/6 - 15/6 W
6 | Meeting with supervisor | 14/6/2019 | 14/6/2019 | bar: 9/6 - 15/6 R
7 | Correction in Chapter 2 writing report | 15/6/19 | 21/6/2019 | bar: 9/6 - 15/6 F to 16/6 - 22/6 R
8 | Meeting with supervisor | 22/6/19 | 22/6/19 | bar: 16/6 - 22/6 F
9 | Correction in Chapter 2 writing report | 23/6/2019 | 18/7/2019 | bar: 23/6 - 29/6 M to 14/7 - 20/7 W
10 | Meeting with supervisor | 19/7/2019 | 19/7/2019 | bar: 14/7 - 20/7 R
11 | Chapter 3 in writing report | 21/7/2019 | 25/7/2019 | bar: 14/7 - 20/7 F to 21/7 - 27/7 M
12 | Chapter 4 in writing report | 26/7/2019 | 29/7/2019 | bar: 21/7 - 27/7 T to 21/7 - 27/7 R
13 | Meeting with supervisor | 30/7/2019 | 30/7/2019 | bar: 21/7 - 27/7 F
14 | Chapter 5 in writing report | 31/7/19 | 2019-04-08 | bar: 28/7 - 3/8 T to 11/8 - 17/8 M
15 | Meeting with supervisor | 2019-05-08 | 2019-05-08 | bar: 11/8 - 17/8 T
16 | Correction in Chapter 5 writing report | 2019-07-08 | 2019-09-08 | bar: 11/8 - 17/8 R
17 | Meeting with supervisor | 2019-12-08 | 2019-12-08 | bar: 11/8 - 17/8 F
16 | FYP submission | 15/8/2019 | 15/8/2019 | bar: 11/8 - 17/8 F